## Risk Register
PEACE IV LOCAL ACTION PLAN
|  |  | PROJECT LEVEL RISK REGISTER: | Shared Spaces Services capital project
Revision Nr - 7
|  |  | Revision Date - Sept 2019 | Note - revisions to actions, risks from previous revision are highlighted bold
Ref | Risk | Risk Type | Detail | Actions | Actions review - status update | Lead / Owner | Likelihood 1-5 | Impact 1-5 | Current Risk Rating | Previous Risk Rating | Status
1 | Failure to drawdown funding within SEUPB budget profiling deadlines due to time delays, resulting in Council having to cover costs. In addition, if there are delays this has implications on claiming programme Secratariat costs, which again has financial implications for Council. Specific time delay causes outlined 1.1 to 1.5 below: | Financial | Current budget profiling was a best estimate. A more detailed investigation is needed around project scope in order to better inform the project spend. In addition if there are delays in drawing capital monies, this is tied to monies apportioned to overall SSS programme, so secretariat (Peace IV staff) funding could also be jeopardised. | 1. Scope of the project to be worked up, detailed and refined. | Closed | PMU (GK lead) | 3 | 5 | 15 | 20 | Complete
|  |  |  | 2. High level costs to be subsequently refined - adjust to within approved costs ie VE exercise if neccesary; engage with other funders/statutory partners to covers costs outside approved budget. BCC are progressing discussions with DfI & DfC regarding additional funding streams | Ongoing | PMU (GK) |  |  |  |  | Ongoing
|  |  |  | 3. Continual review and update budget estimates throughout the project develoment and delivery process (Ongoing) | Ongoing | PMU (GK & QS) |  |  |  |  | Complete, to be reviwed regularly
|  |  |  | 4. Establish SEUPB claims drawdown process and timelines and share with capital project team (both PMU and P&P Finance) | Closed | PIV Team |  |  |  |  | Closed
|  |  |  | 5. Regular budget and finance updates to be reported through Project Goverence structures (Capital Board; Oversight Board; SCP; SEUPB). ICT fee profile included. | Complete, to be reviwed regularly | PMU (GK)
|  |  |  | 6. Procurement Strategy developed to faciliate construction to be progressed in 'works packages' which will faciliate meeting the spend profile | Complete | PMU (GK)
1.1 | Time -delay due to delays around securing landownership agreements (DfC;INI; TNI; Wildlife Trust etc). | Financial and Reputational | The proposed project scope - approximately 12km of connecting pathways to open spaces - covers a range of landowners. To acquire the necessary agreements this will have to go through due process both internal to BCC (assess risks, liabilities, any revenue tail) and other landowners (Deed, legal documentation; negotiation meetings). | 1. Define and agree primary route - identify all landownership; prioritise public ownership route where necessary, and in line with project objectives and outcomes. Primary Route Identifed. BCC Estates Liaising with 3rd Party Landowners | Ongoing | PMU & Estates | 3 | 5 | 15 | 20
|  |  |  | 2. Land assembly process and requirements to feedback into overall capital delivery programme. | Ongoing | PMU (GK)
|  |  |  | 3. Early engagement with identified landowners and stakeholders; maintain communication, engagement and consultation with landowners - Negotiate with relevant landowners to seek early approvals, carry out due diligence - involve legal services | Ongoing | Estates
|  |  |  | 4. Negotiate with landowners to agreed terms; seek committee approval; agree legal documentation and complete process, | Ongoing | Estates
|  |  |  | 5. Report and escalate (via governance structure) known or anticipated delays that will impact on programme delivery, for consideration and agreed action. | Ongoing | Estates
|  |  |  | 6. Clarify procedures & requirements for access to 3rd party lands prior to construction, ie licences agreements etc. DfC Land Transfer Process is being progressed | Ongoing | Estates / KM
1.2 | Project governance - structure is not efficient enough to respond [speedily] to decision making requirements in line with meeting the construction programme. | Programme / Financial | With the Peace programming and capital within one Action Plan, and each historically having independent approval structures (SCP; BCC capital governance), there is a risk of cumbersome structure so the project needs to ensure appropriate authority levels and technical expertise to support efficient decision making. | 1. Develop and agree appropriate governance structure, clarifying all roles and responsibilities; lines of communication; reporting etc; also identify and secure necessary resource and expertise. | Complete | KM & GK - Project Board | 1 | 5 | 5 | 15
|  |  |  | 2. Carry out a review of goverance, particular after keys phases have been completed to consider next stage/phase requirements. Done, BCC have developed governance procedures and will be reviewed during the project | Complete, to be reviwed regularly | PMU (KM lead)
1.3 | Time -delay due to lack of agreement with community stakeholders around Share Spaces usage; which also has implications re outcomes/targets impacts - linked to 7 below. | Financial and Reputational | There is potential financial impact if there are delays, or the programme overruns, given the project location is at the longest interface which has experienced historic community tensions. This creates a cross community challenge, which is one of the driving needs and objectives of the project (peace and reconcillation project objectives). | 1. Develop an appropriate communication, engagement (early engagement) and consultation plan for the project (as per phases; project sections); linked to overall PEACE IV Local Action plan communications and engagement plans. Note Initial Community Engagement Event held 1st Feb 2019. Consultations to be ongoing in line with ICT programme. PACC Event held for Section 2 in Sept 2019. PACC Event for Section 4 scheduled for Nov 2019 | Ongoing | PMU (KM lead) | 3 | 5 | 15 | 15
|  |  |  | 2. Ensure regular community stakeholder reporting [internally] on issues being captured as part of engagement and consultation process; matters to be escalated via project governance as appropriate. | Ongoing | PMU (KM lead)
|  |  |  | 3. Where community issues are raised and identified as outside the scope of physcial project but impact on the funding outcomes, these will be reported to Shared Spaces Steering Group; escalated via project governance (Project Board; Programme Board; SCP; WAWG etc). | Ongoing | PMU (KM lead)
|  |  |  | 4. Consultation Strategy to be developed based on the latest programme for delivery. Statutory Consultations Periods to be included | Ongoing | PMU (KM lead)
1.4 | Time -delay due to delay in securing planning permissions and / or other statutory approvals. | Financial | The proposed project scope - approximately 12km of connecting pathways to open spaces - covers a large geographic area. Seeking and securing all necessary statutory approvals is a requirement to enable delivery. | 1. Refine and establish draft route and concepts proposals so that we know the project scope in order to assess statutory approval implications. | Complete | PMU (GK) | 4 | 5 | 20 | 12
|  |  |  | 2. Maintain communication and liaision with Principle planners for advice and guidance, to then feed into project proposals (design; scheduled/phasing; PAD process). PAD Meetings for S2 & S4 held August 2019. Note - length of time for planning approval process is anticipated to increase given recent experience of Springfield Dam planning process and current timescales for BCC Planning. Nr of planning applications (Major / lighting / signage etc) will have an affect. ICT to ensure robust and comprehensive Planning Applications submitted. | Ongoing | PMU (GK)
|  |  |  | 3. Appoint a competent ICT to undertake statutory approval requirements. | Complete | PMU (SD &GK)
|  |  |  | 4. Early engagement with affected statutory bodies and government programmes (LWWP; Rivers; Roads; DfC; DfI; DoJ etc). | Ongoing | PMU (GK & KM), & ICT
|  |  |  | 5. Develop a project delivery programme that is regularly reviewed to take account of engagement with statutory/planners; any changes or delays to be updated at capital Project Board for oversight. | Ongoing | PMU (GK), & ICT
2 | Project capital costs may escalate as the scheme is at the early stages of development | Financial | Feasibility testing of sites and areas need to be completed, following which subsequent project costs will be assessed and considered. In addition given previous use of the core area of the project (INI Forthriver site/DfC Springvale lands), varying site typography; public liability risks (ie risks in relation to the river through the site) there will be associated costs to address those issues. Undefined at this early stage. | 1. Commission a feasibility study to test route proposals and produce indicative high level cost estimates (due August 2018). | Complete | PMU (GK & SD) | 5 | 5 | 25 | 15
|  |  |  | 2. Once route/scope of works is starting to be defined, carry out necessary land and site surveys, the findings of which to feed into cost estimates. | Ongoing | PMU (GK) & ICT/QS
|  |  |  | 3. Indicative costs to be assessed (ongoing basis) within approved SEUPB budget - necessary action to be taken to bring back into scope (VE; prioritise works, costs etc) within the agreed site selection criteria and project objectives. Note - Cost Reporting is indicating an increase in capital construction costs. Sfield Dam ITT returned above Pre Tender Estimate. VE to be arranged and regular cost meetings required to maintain capital costs within available budget. | Ongoing | PMU (GK & SD) & ICT/QS
|  |  |  | 4. Appoint a cost consultant (QS) for the duration of the project. | Complete | PMU (GK & SD)
|  |  |  | 5.. Regular finance and budget reporting via project governance | Ongoing | PMU (GK)
|  |  |  | 6. ICT to include CostReporting in monthly Progress Report. QS to provide regular reporting | Ongoing | ICT / QS
3 | Failure to acquire necessary land due to legal constraints; lack of agreement/sign off; excessive liabilities, excessive costs (capital/whole life costs) | Land / Programme / Financial | This project spans approx 12km and will cross a number and range of landownerships - early indication shows majority of which is in public sector ownership. However until route is defined and agreed there is an element of unknown (eg no sight of Deeds as of yet). In addition there is an expection that were we may acquire, this would be a nil cost. | 1. Early engagement with identified landowners - Maintain communication; early identification of landowners issues/concerns; provide relevant updates as project is progressing; involve in design consultations. | Ongoing | Estates (ROD) | 3 | 4 | 12 | 12
|  |  |  | 2. Work up the detail of the project scope - check zoning of land; landownership map to be updated and more formalised discussions to be held; review of title (potential restrictions on use) | Ongoing | PMU & Estates
|  |  |  | 3. Ensure appropriate wider community and stakeholder consultation on proposed route to test level of support and evidence benefits/outcomes. | Ongoing | PMU (KM)
|  |  |  | 4. Consider and develop sufficient rational and case for project to inform land assembly negotiations. | Ongoing | Project team
|  |  |  | 5. Close review and input to programme updates as land assembly progress (issues/delays/costs); report and escalate as appropriate to Capital Board; feed into SEUPB reporting requirements. | Ongoing | PMU and Estates
3.1 | Failure to acquire necessary land due to legal constraints; lack of agreement/sign off; excessive liabilities, excessive costs (capital/whole life costs). Risk split into 5 3rd party lands acquistions | Land / Programme / Financial | Bog Meadows | Ongoing engagement with Landowners / Ulster Wildlife Trust. Initial meeting held Jan 2019. | Ongoing | PMU and Estates | 2 | 5 | 10
3.2 |  |  | DfC Lands | Ongoing engagement with Landowners. BCC to arrange meetings in line with project programme | Ongoing | PMU and Estates | 2 | 5 | 10
3.3 |  |  | INI | Ongoing engagement with Landowners. BCC to arrange meetings in line with project programme | Ongoing | PMU and Estates | 2 | 5 | 10
3.6 |  |  | NIHE (Section 1) | Ongoing engagement with Landowners. BCC to arrange meetings in line with project programme | Ongoing | PMU and Estates | 2 | 5 | 10
3.7 |  |  | Education Authority (Section 2) | Ongoing engagement with Landowners. BCC to arrange meetings in line with project programme. | Ongoing | PMU and Estates | 2 | 5 | 10
4 | Failure to achieve the funding drawn down due to non compliance with LoO or ineligible costs eg procurement issues; unforeseen/ unforeseeable arguments; and tight funding claim deadlines; other Funder conflicts (Springfield Dam and Park joint funding) | Financial | The Council is held to strict Letter of Offer requirements, including already established funding drawdown claim deadlines. We must ensure that what is being claimed for is 1) eligible and 2) done so as per drawdown deadlines as per budget profile. NB spend profile was submitted as the best estimate prior to a design team being appointed or any community consutlation taken place. | 1. All officers with budget handling responsibilities to undertake SEUPB finance training. | Complete | PIV Team lead | 2 | 5 | 10 | 15
|  |  |  | 2. Have in place financial protocol to ensure clarity across departments around finance and claimes processes, roles and responsibilities; lines of communication etc. Finance Steering Group has been established | Complete, to be reviwed regularly | PIV Team
|  |  |  | 3. Capital project team to develop and agree with SEUPB Finance control procedures. | Complete | PMU (GK) & ICT
|  |  |  | 4. Establish and communicate clear seperation of DfC and SEUPB funded elements of Springfield Dam Park section of the project; consider tripartide MOU. Cost Consultant to manage and include funding split in Cost Reporting. Licensing Agreements being finalised with DfC | Ongoing | PMU and Estates
|  |  |  | 5. Ensure close monitoring of project finance and budget management, with budget and finance reports included in project governance (Capital Board; Programme Board; Oversight Group; SCP; SP&R). | Ongoing | PMU (GK)
|  |  |  | 6. Capital budget profile to be reviewed and rationale for any changes/adjustments to be recorded and reported to SEUPB. Refer to Action Point Risk 2, AP3 above | Ongoing | PMU (GK)
|  |  |  | 7. BCC to carry out 'Lesson Learnt' exercise based on previous projects and carry forward recommendations as appropriate | Ongoing | PMU (GK)
|  |  |  | 8. ICT preparing Procurement Documentation in line with agreed SEUPB / CPD protocols to ensure prompt approvals and draw down on spend can be achieved | Ongoing | PMU (GK)
5 | Failure to achieve SSS LoO outputs and outcomes due to lack of community appetite; lack of cross community infrastructures in place; lack of community buy in; or failure to design and deliver a capital project that delivers against project objectives. | Programme / Financial | The Council developed a capital project submission for funding of the basis of Belfast Agenda priorities, political support and other sources that evidenced need. However it requires robust and comprehensive cross community engagement to test, inform and agreed the final project to be delivered. | 1. In consultation with relevant internal departments, carry out a stakeholder analysis on the project area. | Complete | PMU (KM lead) | 2 | 5 | 10 | 15
|  |  |  | 2. Develop and agree overall engagement and consultation approach for SSS capital project | Complete | PMU (KM lead)
|  |  |  | 3. Carry out comprehensive engagement (including early engagement) and consultation exercises for the capital build project; findings and feedback to inform capital and programme development. All non-capital related issues to be reported for internal consideration / action as necessary and appropriate. 1st Community Engagement Event held Feb 2019. PACC held in for S2, and planned for S4 in Nov 19 | Ongoing | KM lead
|  |  |  | 4. Develop and agree site selection criteria for capital project; apply to capital and programme development process. Stage 2 Concept Design Report approved and site selection finalised | Complete | Project Board
|  |  |  | 5. Ensure close working between SSS Programming and SSS Capital development and delivery (meetings; updates; identify overlaps/areas of support); consider Benefits realisation exercise to identify roadmap for delivery against outcomes. | Ongoing | Steering Group
|  |  |  | 6. Ensure there is sufficient governance in place to share, report and escalate issues that cross over project delivery areas. | Complete | PIV Programme Board
|  |  |  | 7. As the design process progresses, carry out engagement and consultation exercises that test SS principles and site selection criteria. | Ongoing | PMU (KM lead)
6 | The Council's project contingency ie monies outside of PIV budget contingency] is not sufficient. | Financial | The Council has an approved contingency amount, however if time delay risks, or any of other identified financial risk, escalate and/or are realised this will have an negative impact on the projects affordability and deliverability. | 1. Carry out regular budget reviews and monitoring of costs estimates - engage cost management consultant (QS) to input and review costs as necessary. | Ongoing | PMU (GK) | 5 | 4 | 20 | 8
|  |  |  | 2. Carry out necessary early investigations/sites to identify potential issues and costs (remedial). ICT to advise on required surveys etc | Ongoing | PMU (GK) & ICT
|  |  |  | 3. Review project costs, and where appropriate, identify opportunities to lever in other monies to maximise investment and outcomes. Meeting with DfC arranged to investigate potential additional funding stream | Ongoing | PMU (GK & KM)
|  |  |  | 4. Develop and agree a Change Control procedure with SEUPB | Complete | PMU (GK)
|  |  |  | 5. Ensure ongoing communication with CPD/SEUPB re identified costs | Ongoing | PMU (GK)
|  |  |  | 6. Budget and finance reports to be brought to Capital Board and P&P Oversight Group - early warnings/efficient escalation of issues to be reported in. Procedure Agreed and to be managed accordingly going forward | Complete, to be reviwed regularly | PMU (GK)
|  |  |  | 7. BCC to explore how to access SEUPB OB / Risk Allowance in accordannce with SEUPB LoO | Ongoing | PMU (GK)
|  |  |  | 8. Refer to Risk 2, AP3. Capital Costs have increased. BCC to continue to explore alternative options for new / increased funding streams | Ongoing | PMU (GK)
7 | Risks associated with the procurement of works processes | Financial and Programme | As with any project, potential for cost and programme risks as the projects needs to be worked up and progressed to appropriate design stage. | 1. Develop a Procurement strategy and issue to SEUPB for agreement. | Complete | PMU (GK) | 2 | 4 | 8 | 8
|  |  |  | 2. A procurement timeline to be built into the overall capital delivery programme. | Complete | PMU (GK)
|  |  |  | 3. Follow public procurement and SEUPB procurement guidance - issue all procurement documents to SEUPB (CPD) for review and sign off, prior to commencing any procurement exercise. | Ongoing | PMU (GK, SD, NG)
|  |  |  | 4. SEUPB to review & approve (if appropriate) Procurement Strategy, ICT to manage procurement accordingly and to update Project Programme | Complete | PMU (GK & GK), ICT
8 | On site construction risks - CE; utilities; contractor / sub contractor liquidation / quality; insufficient specification. | Financial / Programme / Quality |  | 1. Procure a competent ICT who will commision sufficient surveys to inform the design development process. | Complete | PMU (GK & SD) | 2 | 4 | 8 | 8
|  |  |  | 2. For contractor procurement, ensure development of robust contract documentation. | Ongoing | PMU (GK, SD, NG), ICT
9 | Design Continuity between Springfield Dam design and rest of scheme, and throughout the scheme | Design / Quality | Two separate Design Teams for Springfield Dam and for remainder of the Scheme. Potential for variance in design. Also potential for variance in construction quality through the main scheme if multiple ISTs are procured with associated potential variance in the supply chain. | 1. Roles and Responsibliites between design teams to be clearly identified. BCC to ensure Design Teams are engaging to ensure designs are consistent | Complete | PMU (GK, SD, NG), ICT | 2 | 4 | 8
|  |  |  | 2. Procurement Strategy developed to ensure consistency in supply chain while also ensuring VFMminimise potential for variance in the supply chains, whil | Complete | PMU (GK), ICT
|  |  |  | 3. ICT to manage IST and to ensure design / construction quality is to the required standard | Ongoing | ICT / QS
10 | Potential for nugatory works if adjacent 3rd party designs / schemes are not considered | Design / Quality / Financial | A number of potential schemes, developed by 3rd parties, have been identifed. These designs will need to be considered so that both 3rd party & SSS Design complement each other. Extent of SSS works to be considered if future schemes overlap with SSS works | 1. Adjacent developments across the SSS Scheme area to be considered and assessed if potential for overlap with SSS scheme | Ongoing | PMU (GK & SD), KM | 2 | 4 | 8
|  |  |  | 1. Ongoing consultatations with 3rd party developers to ensure designs do not clash, and to ensure phasing of works (for either SSS or adjacent development) is managed to avoid nugatory works. | Ongoing | PMU (GK & SD), KM, ICT
11 | Braidwater Housing Proposal | Design / Quality | Braidwater Housing Proposals for S2 have potential to benefit PIV scheme however close co-ordination with respective design teams required to ensure design proposals are consistent and nugatory works are avoided by appropraite phasing of the works | 1. Ongoing meetings to be arranged between ICT and Braidwater Design Team | Ongoing | PMU (GK), KM, ICT | 2 | 4 | 8
CLOSED RISKS
Closed March 2019 | Time -delay due to failure to expedite the procurement process due to BCC procurement frameworks not permitted for use by SEUPB | Financial / Programme | BCC have frameworks in place that can be used to expedite the appointment of designers and help meet SEUPB deadlines. If this approach is not agreed, there will be delays in going through alternative means. | 1. Produce a procurement strategy to be sent to SEUPB (CPD) for sign off. | Closed | PMU (GK) | 1 | 1 | 1 | 12
|  |  |  | 2. Maintain communication and liaision with CPD/ SEUPB | Closed | PMU & PIV (TS, GK, DMcK)
|  |  |  | 3. Once project scope is agreed and delivery approach signed off, procurement requirements to feed into overall delivery programme. | Closed | PMU (GK &SD)
|  |  |  | 4. Carry out all procurement exercises in line with public procurement and SEPUB requirements (ensure staff training on SEUPB requirements). | Closed | PMU (TS)
Closed Sept 2019 | Failure to acquire necessary land due to legal constraints; lack of agreement/sign off; excessive liabilities, excessive costs (capital/whole life costs). Risk split into 5 3rd party lands acquistions | Land / Programme / Financial | Davitts GAC | Ongoing engagement with Landowners. ICT to prepare Options Report for this section of the scheme assessing risks of progressing the requirement for these lands - Lands Omitted | Closed | PMU and Estates & ICT | 1 | 1 | 1
|  |  | Apex Housing | Ongoing engagement with Landowners. ICT to prepare Options Report for this section of the scheme assessing risks of progressing the requirement for these lands - Lands Omitted | Closed | PMU and Estates & ICT | 1 | 1 | 1
Compiled by: | Updated at Risk Workshop, September 2019. Attended by KOS (ICT), GK, ROD (BCC)
Date: | 2019-09-20
Version: | 7

## Risk Matrix Explanation
Risk Likelihood Categories | Score | Risk Impact & Type | Score | Risk Type | Risk Matrix | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Severe (5) | Extreme
Almost Certain | 5 | Insignificant | 1 | Reputational | Almost Certain (5) | 5 | 10 | 15 | 20 | 25 | Very High
Likely | 4 | Minor | 2 | Financial | Likely (4) | 4 | 8 | 12 | 16 | 20 | High
Possible | 3 | Moderate | 3 | HR | Possible (3) | 3 | 6 | 9 | 12 | 15 | Medium
Unlikely | 2 | Major | 4 | Operational | Unlikely (2) | 2 | 4 | 6 | 8 | 10 | Low
Rare | 1 | Severe | 5 | Programme | Rare (1) | 1 | 2 | 3 | 4 | 5 | Very Low